## Timetable
EVENT | TIMETABLE FOR LEVEL B and LEVEL C EVENTS
Event date |  |  |  |  | enter in format dd/mm/yy
|  | Who By? |  |  |  | Printed on | 2021-07-15
BEFORE THE EVENT
Event set-up
Event date agreed with fixtures secretary |  | Fixtures Sec | 540 | -540
Land access permissions all obtained |  | Access liaison | 360 | -360
Plan for map update prepared/mapper booked |  | Mapping Officer | 360 | -360
Organiser identified |  | Chair | 360 | -360
Planner identified |  | Chair | 360 | -360
Controller identified |  | Controller coordinator | 360 | -360
Land use confirmations sent to organiser and planner |  | Access liaison | 180 | -180
Land use restrcitions and conditions noted by all |  | Planner/Organiser | 180 | -180
BOF Risk assessments completed |  | Organiser | 120 | -120
First Aid risk assessment completed |  | Organiser | 120 | -120
Car park identified |  | Access Liaison/Organiser | 120 | -120
Wet weather alternative parking considered |  | Organiser | 120 | -120
Power/water needs clarified |  | Organiser | 120 | -120
Arrange first aid if professional cover considered appropriate |  | Organiser | 120 | -120
Consider if tractor may be needed if bad weather |  | Organiser | 120 | -120
Entry system firm and download arrangements agreed |  | Organiser | 120 | -120
Traders identified |  | Organiser | 120 | -120
Printer identified |  | Mapping Officer | 120 | -120
Entries
Entry system arrangements finalised |  | Organiser | 120 | -120
Fees agreed |  | Organiser | 120 | -120
Flyer developed |  | Organiser | 120 | -120
Details notified to fixtures secretary |  | Organiser | 120 | -120
BO website updated |  | Fixtures Sec |  | 0
Flyer sent to DFOK webmaster |  | Organiser | 100 | -100
Plan for other aspects of event publicity prepared |  | Organiser | 100 | -100
Mapping
Mapping commences |  | Mapping Officer | 120 | -120
Mapping completed |  | Mapping Officer | 60 | -60
Map changes notified to mapping officer |  | Planner | 50 | -50
Mapping officer visits area and makes map changes |  | Mapping Officer | 40 | -40
Updated map sent to Controller |  |  | 30 | -30
Course completion and sign off
Draft courses prepared |  | Planner | 100 | -100
Sites tagged |  | Planner | 90 | -90
Sent to Controller |  | Planner | 90 | -90
Course revisions/discussion with Controller |  | Planner | 70 | -70
Map adjustments notified to mapper |  | Planner | 50 | -50
Map update |  | Mapper | 40 | -40
Updated map received from mapper |  | Planner | 30 | -30
Controller agreement on courses/sites etc |  | Planner | 25 | -25
Controller agreement of updated map |  | Planner | 25 | -25
Control codes, map layout info agreed |  | Planner | 20 | -20
Finalise course OCAD files with Controller |  | Planner | 20 | -20
Control descriptions posted to DFOK website |  | Webmaster | 10 | -10
Entries
Early closing date for entries |  | Organiser | 7 | -7
Matrix for maps tied to entries |  | Organiser | 5 | -5
Appoint jury (level B only) |  | Organiser | 4 | -4
Late entry closing date |  | Organiser | 2 | -2
Map printing
Courses to printers |  | Mapping Officer | 9 | -9
Sample maps received from printers |  | Planner | 7 | -7
Sample maps checked |  | Planner | 7 | -7
Notification of changes to printer |  | Planner | 7 | -7
Corrections from printers |  | Planner | 6 | -6
Checking of corrections |  | Planner | 6 | -6
Print clearance and final numbers agreed |  | Planner/Organiser | 6 | -6
Receipt of printed maps |  | Organiser | 4 | -4
Printed maps checked |  | Organiser | 4 | -4
Errors notified to printers (if necessary) |  | Mapping Officer | 4 | -4
Corrected maps received from printers (unlikely to be needed) |  | Mapping Officer | 2 | -2
Final details
Draft final details |  | Organiser | 20 | -20
Check with Highways Authority re road works |  | Organiser | 20 | -20
Clear with planner |  | Organiser | 15 | -15
Clear with Controller |  | Organiser | 12 | -12
Posted to DFOK website |  | Webmaster | 7 | -7
Manpower
Helpers requirements identified |  | Organiser | 30 | -30
Email to club members notifying them of the Helper discount code |  | Organiser | 30 | -30
Email to all helpers showing everyone's allocation and timings |  | Organiser | 4 | -4
WEEK BEFORE
Equipment needs identified |  | Organiser | 14 | -14
Bales of straw (if needed for any difficult fence crossings) |  | Organiser | 7 | -7
Cones/grit/brush for entrance (Iof needed to ensure no build up of cars) |  | Organiser | 7 | -7
Toilet delivery coordination |  | Organiser | 7 | -7
Confirm all gates openable etc, entry cleared |  | Planner | 7 | -7
Check all fence crossings |  | Planner | 7 | -7
Collection of SI and other equipment |  | Organiser | 7 | -7
Check arrangements with the car park provider etc |  | Organiser | 7 | -7
LAST TWO DAYS BEFORE
Toilets arrive |  | Organiser | 1 | -1
Traders - final confirmation of arrival time/location |  | Organiser | 1 | -1
Safety check and yellow/black tapes out |  | Planner | 1 | -1
Put out some more inaccessible kites and staves |  | Planner | 1 | -1
Controller to check |  | Planner | 1 | -1
Check all signs and notices for the event |  | Organiser | 1 | -1
ON THE DAY
Put out road signs |  | Organiser
Put out remainder of SI units |  | Organiser
Start and finish set up and routes to and from |  | Organiser
Download and enquiries tents |  | Organiser
Results display |  | Organiser
Water.squash |  | Organiser
First aid |  | Organiser
Controllers comments received |  | Organiser
Planners and organisers comments |  | Organiser
Provisional results and comments to website |  | Organiser
AFTER THE DAY
Par times to website |  | Webmaster
Event finance summary received by the Treasurer |  | Organiser
Participation numbers inserted to BO database |  | Fixtures Sec
BO Levy paid |  | Treasurer
SEOA Levy paid (Level B /SE League only) |  | Treasurer
Landowners thanked |  | Access liaison
Equipment returned |  | Organiser
Results finalised |  | Organiser
Ranking list submitted |  | Web